## Tasks Sheet
Task | Owner | Status | Duration | Date Initiated | Date Completed | Comments
Competitor Analysis - Once in a Week
View Detail Page - Revamp | Ashutosh | In Ideation | 9 | 2014-02-17 |  |  | 2014-02-26
Agent Directory | Ashutosh | In Design | 25 | 2014-02-01
List your Property Interface Change in Dashboard | Ashutosh | Completed
Incorporate Select Project Name in List your Property | Ashutosh | Yet to Start
Knowlarity Mobile Verification - SMS, Give Missed Call, Receive Missed Call | Ashutosh | Under Process
IP Verified Packages | Ashutosh | In Process
Elite Property Section + Elite Property View Detail Page | Ashutosh | Yet to Start
Buyer Leads | Ashutosh | In Process
Budget Plan for Marketing of Products | Ashutosh | In Process
Virtual Number Implementation | Ashutosh | More Changes
Virtula Number Agreement Closure and Numbers Procurement | Ashutosh | Waiting for Conf
Paid Listing Validation | Ashutosh | With Tech
Incremental Changes - Hello Popup Property Alert | Ashutosh | Yet to Start
Price Trends | Gunjan
User Interface
Data Clean Up
Data Upload onto Site
Home Loans | Gunjan
ICICI Bank
Featured Banks
Back-End of Home Loans
Vernacular Apps - Language Conversion | Gunjan
Locality Page | Gunjan
Include Google Maps
KYN Ratings Tool Tip
Information Watch out
Locality Comments
Plan to Increase Traffic and Engagement
Incremental Changes | Gunjan
Single Email ID | Dilip
Status on Development |  | In Process
Handholding in all the Screens using Content |  | Yet to Start
Final Verification
Search Result Page | Dilip
List Search Revamp |  | In Design
Map Search Revamp |  | In Design
Google Map Implementation Plan
Check the Complete Dependencies
Property Alert Design Revamp | Dilip | In HTML
WAP Basic Changes | Dilip | Waiting for Tech
MS Listing Integration | Dilip
Take it to Closure
Search Result Null Page UI Re-design | Dilip
Smart Savers | Rangan | Yet to Start
All Projects Info in Top Metros | Rangan | Started
Need to complete it by 8th Mar
Project Names and Builder Names Search | Rangan
Data Pull Up
Data Upload and Live

## Product Log
Module | Product Log | Date Added | Asked By | Team
Email Communication Revamp
SMS Communication Revamp
Mobile No Verification using Knowlarity
CMS for Micro-Sites
Research Reports Section - Front End and Back End
Request Image Workflow
View Detail | Legal Document Download Facility in View Detail Page of the Project
View Detail | Brochure Download Facility in View Detail Page of the Project
Intro Page should be Filled up with Top Metro Information
Chat Now Buddle Should come only after 3 Mins. Once it is closed it should not come in that Session
Smart Savers Platform Should be Out Sourced
Self Service Ad Module should be built for Agents, Individuals and Builders
Interiors / Demo Module should be outsourced
Change the Online Price Model to increase Online Sign-up
IP Rental Strategy, Design and Execution
Option for User to Leave Feedback
View Detail | Follow Builder Feature Built up with good Engagement Elements | 2014-02-24 | Ganesh | Business
View Detail | Chat for Legal Assistance - Chat Widget should come in View Detail Page | 2014-02-24 | Ganesh | Business
| New FAQ Section in the Site by using PhpFAQ Tool | 2014-02-24 | Customers